## Sheet1
			www.goodoldmanoj.com

		Burn down chart

Project	Story	Task	Start	Day 10	Day 9	Day 8	Day 7	Day 6	Day 5	Day 4	Day 3	Day 2	Day 1
	Planning	0.0 Sprint planening	12	12	0	0	0	0	0	0	0	0
Webshop	Logging	1.1 Learn log4java	8	8	8	0	0	0	0	0	0	0	0
Webshop	Logging	1.2 impl. Error	1	1	1	1	0	0	0	0	0	0	0
Webshop	Logging	1.3 impl. Category	3	3	3	1	0	0	0	0	0	0	0
Webshop	Logging	1.4 impl. Product	4	4	4	1	0	0	0	0	0	0	0
Webshop	Logging	1.5 impl. User	3	3	3	0	0	0	0	0	0	0	0
Webshop	Logging	1.6 impl. Shoppingcart	4	4	4	4	0	0	0	0	0	0	0
Webshop	Junit	2.1 Learn Junit	15	15	15	15	15	0	0	0	0	0	0
Webshop	Junit	2.2 test CategoryDAO	8	8	8	8	8	0	0	0	0	0	0
Webshop	Junit	2.3 test ProductDAO	8	8	8	8	8	8	8	4	0	0	0
Webshop	Junit	2.4 test UserDAO	8	8	8	8	8	8	8	4	0	0	0
Webshop	Junit	2.5 ShoppingcartDAO	8	8	8	8	8	8	8	4	0	0	0
Webshop	Books and films	3.1 Design database	6	6	6	0	0	0	0	0	0	0	0
Webshop	Books and films	3.2 Create database	2	2	2	0	0	0	0	0	0	0	0
Webshop	Books and films	3.3 extend product with book class	2	2	2	2	2	0	0	0	0	0	0
Webshop	Books and films	3.4 extend product with film class	2	2	2	2	2	0	0	0	0	0	0
Webshop	Books and films	3.5 create ActorsModel	2	2	2	2	2	0	0	0	0	0	0
Webshop	Books and films	3.6 create AuthorModel	2	2	2	2	2	0	0	0	0	0	0
Webshop	Books and films	3.7 create ActorDAO	4	4	4	4	4	0	0	0	0	0	0
Webshop	Books and films	3.8 create AuthorDAO	4	4	4	4	4	0	0	0	0	0	0
Webshop	Books and films	3.9 integrate film and books to products	3	3	3	3	3	3	0	0	0	0	0
Webshop	Books and films	3.10 test ActorDAO	8	8	8	8	8	8	0	0	0	0	0
Webshop	Books and films	3.11 test AuthorDAO	8	8	8	8	8	8	0	0	0	0	0
Ideal - Remaining efforts in uninterrupted working hours			125	112,5	100	87,5	75	62,5	50	37,5	25	12,5	0
Actual - Remaining efforts in uninterrupted working hours			125	125	113	89	82	43	24	12	0	0	0

Burn down chart