## Sheet1
			www.goodoldmanoj.com

		Burn down chart

Project	Story	Task	Start	Day 10	Day 9	Day 8	Day 7	Day 6	Day 5	Day 4	Day 3	Day 2	Day 1
	Planning	0.0 Sprint planening	12	12	0	0	0
Webshop	Logging	1.1 Learn log4java	8	8	8	0	0
Webshop	Logging	1.2 impl. Error	1	1	1	1	0
Webshop	Logging	1.3 impl. Category	3	3	3	1	0
Webshop	Logging	1.4 impl. Product	4	4	4	1	0
Webshop	Logging	1.5 impl. User	3	3	3	0	0
Webshop	Logging	1.6 impl. Shoppingcart	4	4	4	4	0
Webshop	Junit	2.1 Learn Junit	15	15	15	15	15
Webshop	Junit	2.2 test Category	5	5	5	5	5
Webshop	Junit	2.3 test Product	6	6	6	6	6
Webshop	Junit	2.4 test User	5	5	5	5	5
Webshop	Junit	2.5 Shoppingcart	5	5	5	5	5
Webshop	Books and films	3.1 Design database	6	6	6	6	0
Webshop	Books and films	3.2 Create database	2	2	2	2	0
Webshop	Books and films	3.3 extend product with book class	2	2	2	2	2
Webshop	Books and films	3.3 extend product with film class	2	2	2	2	2
Webshop	Books and films	3.4 create ActorsModel	2	2	2	2	2
Webshop	Books and films	3.5 create AuthorModel	2	2	2	2	2
Webshop	Books and films	3.6 create ActorsDAO	4	4	4	4	4
Webshop	Books and films	3.7 create AuthorDAO	4	4	4	4	4
Webshop	Books and films
Webshop	Books and films
Webshop	Books and films
Webshop	Books and films	14-03-03	2	2	2	2	0
Ideal - Remaining efforts in uninterrupted working hours			97	87,3	77,6	67,9	58,2	48,5	38,8	29,1	19,4	9,7	0
Actual - Remaining efforts in uninterrupted working hours			97	97	85	69	52	0	0	0	0	0	0

Burn down chart